## Product Backlog
Product Backlog — Gyana AI-Powered LMS (Codebase-verified, March 2026)
ID | Epic | User Story | Priority | SP | Status | Sprint | Backend Status | Frontend Status | Notes / Codebase Evidence
PB-01 | Auth | As a user I can log in with username/password and get a JWT token stored in an HTTP-only cookie | Must Have | 3 | Done | S1 | ✅ routes/auth.py /login | ✅ EnhancedLogin.tsx | bcrypt + HS256 JWT, 24h expiry
PB-02 | Auth | As a user I can log out and have my session cleared | Must Have | 1 | Done | S1 | ✅ /logout cookie clear | ✅ Header logout | Cookie cleared on response
PB-03 | Auth | As a user I can change my password after verifying my current password | Must Have | 2 | To Do | S1 | ⚠️ /reset-password exists (token flow) — no in-app change-password endpoint | ❌ No UI in ProfileModal | Password reset via email token only; in-session change not wired
PB-04 | Auth | Email verification on signup | Should Have | 2 | Partial | S1 | ⚠️ /verify-email exists — TODO: email send not implemented | ❌ No email sent; token logged to console | Email send commented out with TODO
PB-05 | Auth | Forgot-password email reset flow | Should Have | 2 | Partial | S1 | ⚠️ /forgot-password exists — token returned in JSON (insecure) | ❌ No reset UI in frontend | TODO: remove token from JSON response; send via email
PB-06 | Auth | Role-based access guards on all API endpoints | Must Have | 3 | Done | S1 | ✅ Depends(get_current_user) + role checks every router | ✅ Protected routes in App.tsx | All 3 roles enforced
PB-07 | Classes | Admin can create classes and sections with an assigned AI chatbot | Must Have | 3 | Done | S2 | ✅ admin.py /classes, /sections, /chatbots | ✅ AdminClassManager.tsx, AdminCourseManager.tsx | Full CRUD available
PB-08 | Classes | Instructor can create their own classes and sections | Must Have | 2 | Done | S2 | ✅ instructor.py /classes, /sections | ✅ EnhancedSectionManager.tsx
PB-09 | Classes | Admin can manage teacher profiles and assign teachers to subjects | Must Have | 3 | Done | S2 | ✅ admin.py /teachers, /teacher-assignments | ✅ AdminTeacherManager.tsx
PB-10 | RAG | Instructor can upload a PDF textbook to create a knowledge base | Must Have | 5 | Done | S3 | ✅ instructor.py /upload-textbook (implied via chatbots) | ✅ Upload UI in instructor panel
PB-11 | RAG | Digital PDFs extracted using Docling (TOC + structured text) | Must Have | 5 | Done | S3 | ✅ utils.py Docling integration | – | arXiv:2501.17887
PB-12 | RAG | Scanned PDFs processed via Tesseract OCR fallback | Must Have | 4 | Done | S3 | ✅ utils.py Tesseract + pdf2image | –
PB-13 | RAG | Text chunked into 1200-token overlapping segments with chapter metadata | Must Have | 3 | Done | S4 | ✅ vectorstore_postgres.py add_documents | – | chunk_size=1200, overlap=150
PB-14 | RAG | 384-dim embeddings generated per chunk (all-MiniLM-L6-v2) | Must Have | 3 | Done | S4 | ✅ models.py singleton SentenceTransformer | –
PB-15 | RAG | Chunks + vectors stored in PostgreSQL document_chunks (pgvector HNSW) | Must Have | 3 | Done | S4 | ✅ vectorstore_postgres.py, pgvector VECTOR(384) | –
PB-16 | Search | BM25 keyword retrieval from document_chunks | Must Have | 3 | Done | S4 | ✅ hybrid_query() bm25_weight param | – | rank-bm25 library
PB-17 | Search | Semantic (cosine) vector retrieval via pgvector | Must Have | 3 | Done | S4 | ✅ hybrid_query() faiss_weight (actually pgvector cosine) | – | FAISS param name kept for compat; actual search is pgvector
PB-18 | Search | Weighted hybrid score fusion (α BM25 + (1-α) semantic) | Must Have | 3 | Done | S4 | ✅ hybrid_query() combine step | – | Default α=0.3 BM25, 0.7 sem
PB-19 | Search | FAISS-based in-memory retrieval for improved recall | Could Have | 4 | Exploring | – | ⚠️ Old FAISS code replaced by pgvector; use_faiss param ignored | – | User wants to re-evaluate FAISS vs pgvector — not yet re-implemented
PB-20 | Chat | Student can ask questions and get grounded answers from their textbook | Must Have | 5 | Done | S5 | ✅ chat.py /chatbots/{id}/chat | ✅ ChatInterface.tsx | SSE streaming
PB-21 | Chat | Responses streamed in real-time via SSE | Should Have | 4 | Done | S5 | ✅ StreamingResponse, text/event-stream | ✅ Token-by-token display in ChatInterface
PB-22 | Chat | Source citations (chapter, page) shown with each answer | Should Have | 3 | Partial | S5 | ⚠️ chunk metadata stored; citation extraction in prompt | ⚠️ Display depends on LLM formatting response correctly | Not always rendered as structured source links
PB-23 | Chat | Knowledge Correction: Instructor flags & corrects AI response | Should Have | 4 | Partial | S5 | ✅ chat.py /feedback/submit — re-indexes to RAG | ❌ No dedicated frontend correction UI found | Backend done; frontend flagging UI not implemented
PB-24 | Enroll | Admin enrolls single student by ID | Must Have | 2 | Done | S6 | ✅ admin.py /sections/{id}/enroll | ✅ AdminEnrollmentCenter.tsx
PB-25 | Enroll | Admin bulk-enrolls students from ID list | Must Have | 3 | Done | S6 | ✅ /sections/{id}/bulk-enroll | ✅ AdminEnrollmentCenter.tsx
PB-26 | Enroll | Admin enrolls students via CSV file upload | Must Have | 3 | To Do | S6 | ❌ No CSV upload endpoint found in admin.py | ❌ No CSV upload UI | Described in report but not implemented in codebase
PB-27 | Enroll | Admin soft-deletes (unenrolls) students preserving audit trail | Must Have | 2 | Done | S6 | ✅ /sections/{id}/students/{student_id} DELETE | ✅ AdminEnrollmentCenter.tsx | enrollment_history endpoint exists
PB-28 | Assignments | Instructor creates assignment (title, desc, due date, rubric, max points) | Must Have | 3 | Done | S6-7 | ✅ instructor.py /assignments/create | ✅ AssignmentManager.tsx | Publish/unpublish supported
PB-29 | Assignments | Student views and submits assignment file | Must Have | 3 | Done | S7 | ✅ student.py /assignments/submit | ✅ StudentAssignmentManager.tsx | PDF/DOCX accepted
PB-30 | Assignments | Instructor views all submissions and grades with feedback | Must Have | 3 | Done | S7 | ✅ /assignments/{id}/submissions + /assignments/grade | ✅ AssignmentSubmissions.tsx, GradeBook.tsx
PB-31 | Assignments | Student views grade and written feedback | Must Have | 2 | Done | S7 | ✅ student.py /grades | ✅ GradeFeedback.tsx
PB-32 | Attendance | Instructor marks attendance per session (Present/Absent/Late/Excused) | Must Have | 3 | Done | S7 | ✅ instructor.py /sections/{id}/attendance POST | ✅ AttendanceManager.tsx
PB-33 | Attendance | Date-range attendance report with CSV export | Should Have | 2 | Partial | S7 | ✅ /sections/{id}/attendance GET with date filter | ⚠️ AttendanceReportView.tsx exists; CSV export button unclear | Report view exists; CSV export not confirmed wired
PB-34 | Content | Instructor generates quiz (MCQ/TF/Short Answer) from chapter | Should Have | 4 | Done | S8 | ✅ /generate-questions + /quizzes/create | ✅ QuizCreator.tsx | Publish/unpublish supported
PB-35 | Content | Student takes quiz and sees score | Should Have | 3 | Done | S8 | ✅ student.py /quizzes/submit | ✅ StudentQuizzes.tsx
PB-36 | Content | Instructor generates flashcard sets | Should Have | 3 | Done | S8 | ✅ /flashcards/generate + /flashcards/save | ✅ FlashcardManager.tsx
PB-37 | Content | Student studies flashcards in flip-card mode | Should Have | 2 | Done | S8 | ✅ student.py /flashcards/{id} | ✅ StudentFlashcards.tsx
PB-38 | Content | Instructor generates lesson plan for a chapter | Should Have | 3 | Done | S8 | ✅ /lesson-plans/generate + save | ✅ LessonPlanner.tsx
PB-39 | Analytics | Instructor views course analytics (avg scores, submission rates) | Should Have | 3 | Done | S8-9 | ✅ /analytics/course/{chatbot_id} | ✅ AnalyticsDashboard.tsx, AssignmentAnalytics.tsx
PB-40 | Analytics | Student views grade timeline and attendance percentage | Should Have | 2 | Done | S8-9 | ✅ student.py /progress, /grades, /progress/timeline | ✅ ProgressTracker.tsx, StudentDashboard.tsx
PB-41 | Resources | Instructor uploads/links course resources (PDF, links) | Could Have | 2 | Done | S9 | ✅ /resources/create + /resources/upload | ✅ CourseResourceLibrary.tsx
PB-42 | Resources | Student views course resource library | Could Have | 1 | Done | S9 | ✅ student.py /resources | ✅ StudentCourseResources.tsx
PB-43 | Testing | Hybrid retrieval evaluation: BM25 vs semantic vs hybrid comparison | Must Have | 5 | In Progress | S10 | ✅ hybrid_query() implemented; α tuning possible | – | Formal evaluation with metrics (Hit Rate, MRR) not yet documented
PB-44 | Testing | FAISS vs pgvector retrieval investigation | Could Have | 4 | Exploring | – | ⚠️ pgvector in use; FAISS replaced — re-evaluation not done | – | User wants to try FAISS again for potential recall improvement
PB-45 | Testing | Final UAT: Admin, Instructor, Student full flows | Must Have | 3 | In Progress | S10-13 | Manual testing ongoing | –
PB-46 | Report | Complete FYP final report (all chapters) | Must Have | 5 | In Progress | S10-13 | – | – | Ch 1-10 written; Ch 11 (Conclusion) pending
LEGEND — Priority: 🔴 Must Have 🟠 Should Have 🔵 Could Have ¦ Status: 🟢 Done 🟠 In Progress 🟡 Partial ⚫ To Do 🔬 Exploring

## Summary
Project Status Summary — Gyana LMS (March 2026)
Category | Total Items | ✅ Done | ⚠️ Partial / In Progress / Exploring | ❌ To Do
Authentication | 6 | 3 | 2 | 1
Class Management | 3 | 3 | 0 | 0
RAG Pipeline | 6 | 6 | 0 | 0
Hybrid Search | 4 | 3 | 1 | 0
AI Chatbot | 4 | 2 | 2 | 0
Enrollment | 4 | 3 | 0 | 1
Assignments | 4 | 4 | 0 | 0
Attendance | 2 | 1 | 1 | 0
AI Content Gen | 5 | 5 | 0 | 0
Analytics | 2 | 2 | 0 | 0
Resources | 2 | 2 | 0 | 0
Testing / Eval | 3 | 0 | 3 | 0
Report Writing | 1 | 0 | 1 | 0
Known Gaps & In-Progress Items (from codebase analysis)
Issue / Gap | Description | Area | Status | Recommended Action
In-session change-password | Password reset via email token only — no /change-password for logged-in users | Auth | To Do | Add POST /auth/change-password + ProfileModal UI
Email sending (verify/forgot) | Token returned in JSON body (TODO comment in code) — email not sent | Auth | To Do | Integrate SMTP / SendGrid
CSV enrollment upload | Endpoint described in report but not found in admin.py codebase | Enrollment | To Do | Add /admin/sections/{id}/csv-enroll endpoint + UI
KnowledgeCorrection UI | Backend /feedback/submit works; no frontend flagging component exists | Correction | To Do | Build FlagResponseModal in ChatInterface
FAISS vs pgvector recall | User wants to re-evaluate FAISS for retrieval; currently pgvector only | Search | Exploring | Implement FAISS PoC branch; measure Hit Rate + MRR vs pgvector
Source citation rendering | Citations stored in metadata; rendering depends on LLM output format | Chat UI | To Do | Parse [Source: chapter, p.X] tokens and render as structured links
Attendance CSV export | AttendanceReportView.tsx exists; CSV export button not confirmed wired | Attendance | Partial | Wire export button to /attendance/report?format=csv
Formal retrieval evaluation | Academic chapter requires Hit Rate, MRR, Faithfulness metrics documented | Testing | In Progress | Build eval script with 20+ test queries across subjects
Chapter 11: Conclusion | Final report chapter not written | Report | To Do | Write after evaluation complete

## Sprint 1
Sprint Backlog — Sprint 1 ¦ Oct Wk 1–2, 2025
Sprint Goal: Authentication & RBAC — secure login, JWT, role guards
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-01 | Set up FastAPI project structure, PostgreSQL schema, Python venv | Infra | 3 | Done | routes/ and DB tables created
T-02 | Create users table with role field; bcrypt password hashing | DB / Auth | 2 | Done | passlib[bcrypt] used
T-03 | Implement /auth/login — bcrypt verify, JWT issue (HS256, 24h) | Auth | 2 | Done | HTTP-only cookie set
T-04 | Implement /auth/logout — cookie clear | Auth | 1 | Done
T-05 | JWT middleware: get_current_user() FastAPI dependency | Auth | 2 | Done | utils_auth.py
T-06 | Role guards: 403 Forbidden for wrong-role access | RBAC | 2 | Done | All routers protected
T-07 | In-session change-password endpoint (authenticated user) | Auth | 2 | To Do | Only token-based reset exists; no in-session /change-password
T-08 | Email send for verify-email and forgot-password | Auth | 3 | To Do | TODO comment in code — token returned in JSON currently
Total SP: 17 ¦ Completed: 12 SP ¦ Remaining: 5 SP ¦ Velocity: 12/17

## Sprint 2
Sprint Backlog — Sprint 2 ¦ Oct Wk 3 – Nov Wk 1, 2025
Sprint Goal: Class & Section Management — multi-tenant structure
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-09 | Create institutions, classes, sections, chatbots DB tables | DB | 3 | Done
T-10 | Admin: create/update/delete classes and sections | Admin API | 3 | Done | admin.py full CRUD
T-11 | Admin: manage teachers; assign subject teachers | Admin API | 3 | Done | AdminTeacherManager.tsx
T-12 | Admin: create chatbots (AI knowledge bases) per course | Admin API | 2 | Done | /admin/chatbots
T-13 | React frontend: Login UI, role-based routing, protected routes | Frontend | 3 | Done | App.tsx routes
T-14 | Instructor: create class and section | Instructor API | 2 | Done | instructor.py (deprecated wrappers kept)
Total SP: 16 ¦ Completed: 16 SP ¦ Remaining: 0 SP ¦ Velocity: 16/16

## Sprint 3
Sprint Backlog — Sprint 3 ¦ Nov Wk 1–2, 2025
Sprint Goal: OCR Pipeline — PDF ingestion, Docling + Tesseract extraction
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-15 | Docling integration for digital PDF text + TOC extraction | OCR | 5 | Done | utils.py Docling pipeline
T-16 | Tesseract + pdf2image for scanned-page OCR fallback | OCR | 4 | Done | Page-type routing
T-17 | documents DB table; textbook upload endpoint | DB / API | 2 | Done
T-18 | Instructor PDF upload UI | Frontend | 2 | Done
Total SP: 13 ¦ Completed: 13 SP ¦ Remaining: 0 SP ¦ Velocity: 13/13

## Sprint 4
Sprint Backlog — Sprint 4 ¦ Nov Wk 3 – Dec Wk 2, 2025
Sprint Goal: Chunking, Embeddings & Hybrid Search
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-19 | Overlapping text chunking (1200 tok, 150 overlap) with chapter metadata | RAG | 3 | Done
T-20 | all-MiniLM-L6-v2 singleton model loader | Embedding | 2 | Done | models.py
T-21 | pgvector setup: VECTOR(384), HNSW index | DB | 3 | Done | document_chunks table
T-22 | BM25 retrieval via rank-bm25 | Search | 3 | Done | bm25_weight param in hybrid_query()
T-23 | Semantic cosine retrieval via pgvector | Search | 2 | Done | faiss_weight param (actually pgvector)
T-24 | Hybrid score fusion: α × BM25 + (1-α) × cosine | Search | 3 | Done | Default 0.3/0.7
T-25 | FAISS in-memory index investigation (alternative to pgvector) | Research | 4 | Exploring | Previous FAISS code replaced; user wants to re-evaluate recall improvement
Total SP: 20 ¦ Completed: 16 SP ¦ Remaining: 4 SP ¦ Velocity: 16/20

## Sprint 5
Sprint Backlog — Sprint 5 ¦ Dec Wk 3 – Jan Wk 1, 2026
Sprint Goal: RAG Chatbot, Groq LLM & SSE Streaming
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-26 | Groq API integration (Llama 3.3 70B) | LLM | 2 | Done | call_groq_llm() in chat.py
T-27 | Grounded prompt construction (system + chunks + query) | Prompt | 3 | Done | classify_query() + prompt builder
T-28 | SSE streaming endpoint /chatbots/{id}/chat | Chat API | 4 | Done | StreamingResponse
T-29 | Source citation extraction from chunk metadata | RAG | 2 | Partial | Stored in DB; display relies on LLM response format — not always rendered as links
T-30 | Student real-time chat UI | Frontend | 4 | Done | ChatInterface.tsx
T-31 | Knowledge Correction: /feedback/submit re-indexes corrected answer | Correction | 3 | Partial | Backend done (add_feedback_document); no frontend flagging UI built
Total SP: 18 ¦ Completed: 13 SP ¦ Remaining: 5 SP ¦ Velocity: 13/18

## Sprint 6
Sprint Backlog — Sprint 6 ¦ Jan Wk 1–2, 2026
Sprint Goal: Enrollment Management System
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-32 | enrollments + enrollment_history DB tables with soft-delete | DB | 2 | Done
T-33 | Admin: single student enrollment + unenroll | Admin API | 2 | Done
T-34 | Admin: bulk enrollment from ID list | Admin API | 2 | Done
T-35 | Admin: CSV file enrollment upload | Admin API | 3 | To Do | Not found in admin.py — endpoint missing
T-36 | Enrollment audit trail / history view | Admin API | 2 | Done | /enrollment-history endpoint exists
T-37 | Admin Enrollment Center UI | Frontend | 3 | Done | AdminEnrollmentCenter.tsx
Total SP: 14 ¦ Completed: 11 SP ¦ Remaining: 3 SP ¦ Velocity: 11/14

## Sprint 7
Sprint Backlog — Sprint 7 ¦ Jan Wk 2–3, 2026
Sprint Goal: Assignment Management & Attendance Tracking
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-38 | assignments + assignment_submissions DB tables | DB | 2 | Done
T-39 | Instructor: create/publish/delete assignment | Instructor API | 3 | Done | AssignmentManager.tsx
T-40 | Student: view assignments + submit file | Student API | 3 | Done | StudentAssignmentManager.tsx
T-41 | Instructor: view submissions + grade + feedback | Instructor API | 3 | Done | AssignmentSubmissions.tsx, GradeBook.tsx
T-42 | Student: view grade and feedback | Student API | 2 | Done | GradeFeedback.tsx
T-43 | Instructor: mark attendance per session (bulk) | Attendance | 3 | Done | /sections/{id}/attendance POST
T-44 | Attendance report GET + date filter | Attendance | 2 | Done | date param in GET
T-45 | CSV export of attendance report | Attendance | 2 | Partial | AttendanceReportView.tsx exists; CSV export button not confirmed wired to backend
Total SP: 20 ¦ Completed: 18 SP ¦ Remaining: 2 SP ¦ Velocity: 18/20

## Sprint 8
Sprint Backlog — Sprint 8 ¦ Jan Wk 4 – Feb Wk 2, 2026
Sprint Goal: AI Content Generation Suite & Analytics
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-46 | Quiz generation (MCQ, TF, Short Answer) from textbook chapter | Content Gen | 3 | Done | QuizCreator.tsx
T-47 | Student takes quiz + score shown | Content Gen | 3 | Done | StudentQuizzes.tsx
T-48 | Flashcard generation + student flip-card study | Content Gen | 3 | Done | FlashcardManager.tsx + StudentFlashcards.tsx
T-49 | Lesson plan generation from chapter | Content Gen | 3 | Done | LessonPlanner.tsx
T-50 | Instructor course analytics (scores, submission rates) | Analytics | 3 | Done | AnalyticsDashboard.tsx
T-51 | Student progress / grade timeline | Analytics | 2 | Done | ProgressTracker.tsx
T-52 | Course resource library (upload + link) | Resources | 2 | Done | CourseResourceLibrary.tsx
Total SP: 19 ¦ Completed: 19 SP ¦ Remaining: 0 SP ¦ Velocity: 19/19

## Sprint 9
Sprint Backlog — Sprint 9 ¦ Feb Wk 2–3, 2026
Sprint Goal: Knowledge Correction, Resources & Integration Testing
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-53 | Backend: /feedback/submit re-indexes corrected answer | Correction | 3 | Done | add_feedback_document() in vectorstore_postgres.py
T-54 | Frontend: flagging/correction UI for instructor | Correction | 3 | To Do | No component found — backend ready but UI not built
T-55 | End-to-end RAG chatbot testing with real textbooks | Testing | 3 | In Progress | Manual tests; no automated eval suite yet
T-56 | Security testing: JWT expiry, RBAC violations, file upload | Testing | 3 | In Progress | Manual Postman tests
Total SP: 12 ¦ Completed: 3 SP ¦ Remaining: 9 SP ¦ Velocity: 3/12

## Sprint 10–13
Sprint Backlog — Sprint 10–13 ¦ Feb Wk 4 – May 2026
Sprint Goal: Evaluation, FAISS PoC, Remaining Features & Final Submission
Task ID | Epic / Area | Task Description | SP | Status | Codebase / Notes
T-57 | In-session change-password endpoint + ProfileModal UI | Auth | 2 | To Do | Missing: only token-reset flow exists
T-58 | Wire email sending for verify-email and forgot-password | Auth | 3 | To Do | TODO in auth.py — needs SMTP/SendGrid integration
T-59 | CSV enrollment upload endpoint + UI | Enroll | 3 | To Do | Missing from admin.py
T-60 | Knowledge Correction flagging UI for instructor | Correction | 3 | To Do | Backend ready; no frontend component
T-61 | Attendance CSV export: confirm and wire button to backend | Attendance | 1 | To Do
T-62 | FAISS PoC: evaluate FAISS recall vs pgvector for hybrid search | Research | 4 | Exploring | User not satisfied with current retrieval — exploring FAISS for improved recall
T-63 | Citation display: render source links as structured refs in chat UI | Chat UI | 2 | To Do | Currently LLM-format dependent
T-64 | Formal retrieval evaluation: Hit Rate, MRR, Faithfulness scoring | Evaluation | 5 | In Progress | Academic question chapter requires these metrics
T-65 | UAT: full Admin, Instructor, Student session walkthroughs | Testing | 3 | In Progress
T-66 | Write Chapter 11: Conclusion + evaluation results | Report | 3 | To Do | Final chapter pending
T-67 | Final proof-read, formatting, artefact zip + submission | Report | 2 | To Do
Total SP: 31 ¦ Completed: 0 SP ¦ Remaining: 31 SP ¦ Velocity: 0/31